## Gantt Chart
Dream Team
| To Do | Done This Week | Scheduled for Next Week | Done Previously
Color Codes
| Task: | Predecessor: | Duration | Actual: Hours | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
| 1. TF Requirement Collection | - | 10 | 10 | bar: Week 1 to Week 2
| 2. TF Layout Per Level | 1 | 15 | 12 | bar: Week 3 to Week 5
| 3. TF Doors & Traps | 1,2 | 15 | 14 | bar: Week 6 to Week 7
| 4. TF Item Placement | 1,2 | 10 | 8 | bar: Week 6 to Week 7
| 5. TF Music Discovery | - | 10 | 4 | bar: Week 1 to Week 2
| 6. TF Programming | 2,3,4,5 | 20 | bar: Week 8 to Week 11
| 7. TF Testing | 6 | 5 | bar: Week 12
| 8. TF Installation | 5,7 | 5 | bar: Week 13
|  | Predecessor: | Duration | Actual: Hours
| 1. JM Requirements Collection | - | 20 | 5 | bar: Week 1 to Week 4
| 2. JM Screen Design | 1 | 10 | 3 | bar: Week 5 to Week 6
| 3. JM Prototype Design | 1 | 10 | 2 | bar: Week 5 to Week 6
| 4. JM Database Construction | 2,3 | 10 | 4 | bar: Week 7 to Week 8
| 5. JM Coding/Documentation | 4 | 10 | 3 | bar: Week 9 to Week 14
| 6. JM Programming | 4 | 15 | 14 | bar: Week 11 to Week 13
| 7. JM Testing | 6 | 5 | 2 | bar: Week 14
| 8. JM Installation | 5,7 | 5 | bar: Week 15
|  | Predecessor: | Duration | Actual: Hours
| 1. EV Software Analysis | - | 8 | 8 | bar: Week 1 to Week 2
| 2. EV Enemy Design and Animation | 1 | 10 | 9 | bar: Week 3 to Week 4
| 3. EV Enemy Movement | 2 | 10 | 13 | bar: Week 5 to Week 6
| 4. EV Implement Spawn/ Smarter Enemies | 3 | 15 | bar: Week 7 to Week 9
| 5. EV Documentation | 4 | 10 | 8 | bar: Week 10 to Week 11
| 6. EV Testing | 5 | 10 | 5 | bar: Week 12 to Week 13
|  | Predecessor: | Duration | Actual: Hours
| 1. LB Environment Setup | - | 4 | 6 | bar: Week 1 to Week 2
| 2. LB Bot Design | - | 5 | 2 | bar: Week 1 to Week 2
| 3. LB Gather Unit Tests | - | 2 | 2 | bar: Week 1
| 4. LB Program Bot | 1,2 | 12 | bar: Week 3 to Week 6
| 5. LB Structure Unit Tests | 1,3 | 4 | 4 | bar: Week 2 to Week 3
| 6. LB Program Unit Test | 5 | 9 | bar: Week 4 to Week 6
| 7. LB Program Cheats | 1 | 8 | 6 | bar: Week 2 to Week 4
| 8. LB Bot Testing | 4 | 4 | bar: Week 7 to Week 9
| 9. LB Unit Test Testing | 6 | 4 | bar: Week 7 to Week 9
| 10. LB Cheat Testing | 7 | 5 | bar: Week 5 to Week 6
|  | Predecessor: | Duration | Actual: Hours
| 1. BW Requirements Collection | - | 10 | 16 | bar: Week 1 to Week 2
| 2. BW Setup Player Gameobject | 1 | 5 | 3 | bar: Week 3
| 3. BW Create Movement Controller | 2 | 15 | 7 | bar: Week 4 to Week 6
| 4. BW Create Camera Controller | 2 | 15 | 5 | bar: Week 4 to Week 6
| 5. BW Create Interaction Controller | 2 | 15 | bar: Week 4 to Week 6
| 6. BW Unit Testing | 3,4,5 | 15 | bar: Week 7 to Week 9
| 7. BW Integration Testing | 3,4,5 | 10 | 6 | bar: Week 10 to Week 11

## Hours Cost
Brad W. | Estimated Hours | Actual Hours
1. BW Requirements Collection | 10 | 16
2. BW Setup Player Gameobject | 5 | 3
3. BW Create Movement Controller | 15 | 7
4. BW Create Camera Controller | 15 | 5
5. BW Create Interaction Controller | 15
6. BW Unit Testing | 15
7. BW Integration Testing | 10 | 6
Jorge M. | Estimated Hours | Actual Hours
1. Requirements Collection | 20 | 5
2. Screen Design | 10 | 3
3. Prototype Design | 10 | 2
4. Database Construction | 10 | 4
5. Coding/Documentation | 10 | 3
6. Programming | 15 | 14
7. Testing | 5 | 2
8. Installation | 5
Luke B. | Estimated Hours | Actual Hours
1. Environment Setup | 4 | 6
2. Bot Design | 5 | 2
3. Gather Unit Tests | 2 | 2
4. Program Bot | 12
5. Structure Unit Tests | 4 | 4
6. Program Unit Test | 9
7. Program Cheats | 8 | 6
8. Bot Testing | 4
9. Unit Test Testing | 4
10. Cheat Testing | 5
Edgar V. | Estimated Hours | Actual Hours
1. Software Analysis | 8 | 8
2. Enemy Design and Animation | 10 | 9
3. Enemy Movement | 10 | 13
4. Implement Spawn/ Smarter Enemies | 15
5. Documentation | 10 | 8
6. Testing | 10 | 5
Tyler F. | Estimated Hours | Actual Hours
1. Requirement Collection | 10 | 10
2. Layout Per Level | 15 | 12
3. Doors & Traps | 15 | 14
4. Item Placement | 10 | 8
5. Music Discovery | 10 | 4
6. Programming | 20
7. Testing | 5
8. Installation | 5
| Total Estimated Hours | Total Actual Hours | Estimated Cost | Actual Cost
| 380 | 181 | 38000 | 18100