## Sheet1
Dream Team
Task: | Duration | Predecessor: | Actual: Hours | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
1. TF Requirement Collection | 10 | - | bar: Week 1 to Week 2
2. TF Layout Per Level | 15 | 1 | bar: Week 3 to Week 5
3. TF Doors & Traps | 15 | 1,2 | bar: Week 6 to Week 7
4. TF Item Placement | 10 | 1,2 | bar: Week 6 to Week 7
5. TF Music Discovery | 10 | - | bar: Week 1 to Week 2
6. TF Programming | 20 | 2,3,4,5 | bar: Week 8 to Week 11
7. TF Testing | 5 | 6 | bar: Week 12
8. TF Installation | 5 | 5,7 | bar: Week 13
1. JM Requirements Collection | 20 | - | bar: Week 1 to Week 4
2. JM Screen Design | 10 | 1 | bar: Week 5 to Week 6
3. JM Prototype Design | 10 | 1 | bar: Week 5 to Week 6
4. JM Database Construction | 10 | 2,3 | bar: Week 7 to Week 8
5. JM Coding/Documentation | 10 | 4 | bar: Week 9 to Week 14
6. JM Programming | 15 | 4 | bar: Week 11 to Week 13
7. JM Testing | 5 | 6 | bar: Week 14
8. JM Installation | 5 | 5,7 | bar: Week 15
1. EV Software Analysis` | 8 | - | bar: Week 1 to Week 2
2. EV Enemy Design | 10 | 1 | bar: Week 3 to Week 4
3. EV Enemy Movement | 10 | 2 | bar: Week 5 to Week 6
4. EV Implement Spawn | 15 | 3 | bar: Week 7 to Week 9
5. EV Documentation | 10 | 4 | bar: Week 10 to Week 11
6. EV Testing | 10 | 5 | bar: Week 12 to Week 13
1. LB Environment Setup | 4 | - | bar: Week 1 to Week 2
2. LB Bot Design | 5 | - | bar: Week 1 to Week 2
3. LB Gather Unit Tests | 2 | - | bar: Week 1
4. LB Program Bot | 12 | 1,2 | bar: Week 3 to Week 6
5. LB Structure Unit Tests | 4 | 1,3 | bar: Week 2 to Week 3
6. LB Program Unit Test | 9 | 5 | bar: Week 4 to Week 6
7. LB Program Cheats | 8 | 1 | bar: Week 2 to Week 4
8. LB Bot Testing | 4 | 4 | bar: Week 7 to Week 9
9. LB Unit Test Testing | 4 | 6 | bar: Week 7 to Week 9
10. LB Cheat Testing | 5 | 7 | bar: Week 5 to Week 6
1. BW Requirements Collection | 10 | - | bar: Week 1 to Week 2
2. BW Setup Player Gameobject | 5 | 1 | bar: Week 3
3. BW Create Movement Controller | 15 | 2 | bar: Week 4 to Week 6
4. BW Create Interaction Controller | 15 | 2 | bar: Week 4 to Week 6
5. BW Unit Testing | 15 | 3,4 | bar: Week 7 to Week 9
6. BW Integration Testing | 10 | 5 | bar: Week 10 to Week 11